## Product Backlog
Story ID | Story Title | Priority | Story Points | Assigned To | Status | Start Date | End Date | Remarks
1 | User Registration & Login | High | 5 | Sahaji Chaurasia | Completed | 25-Oct-2025 | 26-Oct-2025 | Implemented JWT-based auth
2 | Artist Profile Creation | Medium | 3 | Sahaji Chaurasia | Completed | 26-Oct-2025 | 27-Oct-2025 | Created profile model and routes
3 | Artwork Upload & Management | High | 4 | Sahaji Chaurasia | Completed | 27-Oct-2025 | 28-Oct-2025 | Added artwork upload API
4 | Artwork Search & Discovery | Low | 2 | Sahaji Chaurasia | Completed | 28-Oct-2025 | 29-Oct-2025 | Search filters integrated
5 | Purchase Flow Integration | Medium | 3 | Sahaji Chaurasia | Completed | 29-Oct-2025 | 30-Oct-2025 | Checkout flow implemented
6 | Dashboard & Analytics | High | 4 | Sahaji Chaurasia | Completed | 30-Oct-2025 | 31-Oct-2025 | Analytics dashboard built
7 | Community & Collaboration | Low | 3 | Sahaji Chaurasia | In Progress | 31-Oct-2025 | 03-Nov-2025 | Community module under dev

## Backlog Grooming
Story ID | Grooming Notes | Dependencies | Refined Story Points | Ready for Sprint
1 | Confirmed API contract for user auth | Database schema finalized | 5 | Yes
2 | Added bio and art style fields | UI component delivery pending | 3 | Yes
3 | Ensured image compression and metadata tagging | Cloud storage setup required | 4 | Yes
4 | Reviewed ElasticSearch integration feasibility | Search API endpoint needed | 3 | Yes
5 | Discussed Razorpay integration readiness | Payment gateway testing pending | 4 | Yes
6 | Added metrics for sales & traffic | Data aggregation from order service | 4 | Yes
7 | Planned WebSocket-based live chat | Socket server configuration | 3 | Yes

## Sprint 1 Backlog
Task Description | Status | Start Date | End Date | Assignee
Setup project & environment | Completed | 25-Oct-2025 | 25-Oct-2025 | Sahaji Chaurasia
Implement user registration/login APIs | Completed | 25-Oct-2025 | 26-Oct-2025 | Sahaji Chaurasia
Setup MongoDB models and relations | Completed | 26-Oct-2025 | 27-Oct-2025 | Sahaji Chaurasia
Create artist profile endpoints | Completed | 27-Oct-2025 | 28-Oct-2025 | Sahaji Chaurasia
Add artwork upload and storage logic | Completed | 28-Oct-2025 | 29-Oct-2025 | Sahaji Chaurasia
Test routes using Postman | Completed | 29-Oct-2025 | 29-Oct-2025 | Sahaji Chaurasia
Fix validation and auth middleware bugs | Completed | 30-Oct-2025 | 30-Oct-2025 | Sahaji Chaurasia
Write unit tests for auth module | Completed | 30-Oct-2025 | 31-Oct-2025 | Sahaji Chaurasia
Review and merge sprint 1 PRs | Completed | 31-Oct-2025 | 31-Oct-2025 | Sahaji Chaurasia

## Sprint 2 Backlog
Task Description | Status | Start Date | End Date | Assignee
Develop artwork search and filter APIs | Completed | 01-Nov-2025 | 01-Nov-2025 | Sahaji Chaurasia
Integrate frontend search UI with backend | Completed | 01-Nov-2025 | 02-Nov-2025 | Sahaji Chaurasia
Implement purchase and payment flow | Completed | 02-Nov-2025 | 02-Nov-2025 | Sahaji Chaurasia
Add dashboard analytics charts | Completed | 02-Nov-2025 | 02-Nov-2025 | Sahaji Chaurasia
Setup community chat endpoints | In Progress | 02-Nov-2025 | 03-Nov-2025 | Sahaji Chaurasia
Test dashboard stats accuracy | Completed | 02-Nov-2025 | 02-Nov-2025 | Sahaji Chaurasia
Fix UI bugs from sprint review | Completed | 03-Nov-2025 | 03-Nov-2025 | Sahaji Chaurasia
Prepare release build and documentation | Completed | 03-Nov-2025 | 03-Nov-2025 | Sahaji Chaurasia

## Daily Stand-up Log
Date | Day | Team Member | Work Done | Blockers | Status
25-Oct-2025 | Day 1 | Sahaji Chaurasia | Progressed work on backend & UI integration (Sprint 1) | None | Completed
26-Oct-2025 | Day 2 | Sahaji Chaurasia | Progressed work on backend & UI integration (Sprint 1) | None | Completed
27-Oct-2025 | Day 3 | Sahaji Chaurasia | Progressed work on backend & UI integration (Sprint 1) | None | Completed
28-Oct-2025 | Day 4 | Sahaji Chaurasia | Progressed work on backend & UI integration (Sprint 1) | None | Completed
29-Oct-2025 | Day 5 | Sahaji Chaurasia | Progressed work on backend & UI integration (Sprint 1) | None | Completed
30-Oct-2025 | Day 6 | Sahaji Chaurasia | Progressed work on backend & UI integration (Sprint 2) | None | Completed
31-Oct-2025 | Day 7 | Sahaji Chaurasia | Progressed work on backend & UI integration (Sprint 2) | None | Completed
01-Nov-2025 | Day 8 | Sahaji Chaurasia | Progressed work on backend & UI integration (Sprint 2) | Minor API sync issue | Completed
02-Nov-2025 | Day 9 | Sahaji Chaurasia | Progressed work on backend & UI integration (Sprint 2) | None | In Progress

## Retrospection
What Went Well | What Didn't Go Well | Action Items for Next Sprint
Consistent daily commits and progress | Minor time overruns during testing | Improve documentation clarity
Backend and UI integrated smoothly | API integration took longer than planned | Add buffer time for testing
Effective testing before deployment | Some validation edge cases missed | Automate deployment to avoid delays
Timely completion of sprint goals | Limited peer review due to solo dev | Enhance UI accessibility features