## Product Backlog
Story ID | Story Title | Priority | Story Points | Status | Start Date | End Date | Assignee | Description
1 | User Registration & Login | High | 3 | Completed | 25-Oct-2025 | 26-Oct-2025 | Sahaji Chaurasia | Allow users to register and login securely
2 | Artist Profile Creation | Medium | 6 | Completed | 26-Oct-2025 | 27-Oct-2025 | Sahaji Chaurasia | Artists can create and manage their profiles
3 | Artwork Upload & Management | High | 9 | Completed | 27-Oct-2025 | 28-Oct-2025 | Sahaji Chaurasia | Artists can upload and manage artwork listings
4 | Artwork Search & Discovery | Low | 12 | Completed | 28-Oct-2025 | 29-Oct-2025 | Sahaji Chaurasia | Buyers can search and filter artworks
5 | Purchase Flow | Medium | 15 | Completed | 29-Oct-2025 | 30-Oct-2025 | Sahaji Chaurasia | Buyers can purchase artworks securely
6 | Dashboard & Analytics | High | 18 | Completed | 30-Oct-2025 | 31-Oct-2025 | Sahaji Chaurasia | Artists can view performance analytics
7 | Community & Collaboration | Low | 21 | In Progress | 31-Oct-2025 | 01-Nov-2025 | Sahaji Chaurasia | Artists can interact and share ideas

## Product Backlog Grooming
Story ID | Story Title | Refinement Notes | Dependencies | Estimate Confidence | Sprint Allocation | Reviewed By
1 | User Registration & Login | Reviewed functionality for user registration & login. Dependencies mapped. | Database, Auth Service | High | Sprint 1 | Sahaji Chaurasia
2 | Artist Profile Creation | Reviewed functionality for artist profile creation. Dependencies mapped. | Database, Auth Service | High | Sprint 1 | Sahaji Chaurasia
3 | Artwork Upload & Management | Reviewed functionality for artwork upload & management. Dependencies mapped. | Database, Auth Service | High | Sprint 1 | Sahaji Chaurasia
4 | Artwork Search & Discovery | Reviewed functionality for artwork search & discovery. Dependencies mapped. | Payment Gateway, Notification Service | High | Sprint 2 | Sahaji Chaurasia
5 | Purchase Flow | Reviewed functionality for purchase flow. Dependencies mapped. | Payment Gateway, Notification Service | Medium | Sprint 2 | Sahaji Chaurasia
6 | Dashboard & Analytics | Reviewed functionality for dashboard & analytics. Dependencies mapped. | Payment Gateway, Notification Service | Medium | Sprint 2 | Sahaji Chaurasia
7 | Community & Collaboration | Reviewed functionality for community & collaboration. Dependencies mapped. | Payment Gateway, Notification Service | Medium | Sprint 2 | Sahaji Chaurasia

## Sprint 1 Backlog
Story ID | Task | Assignee | Status | Start Date | End Date
1 | Setup project, initialize repo | Sahaji Chaurasia | Completed | 25-Oct-2025 | 29-Oct-2025
1 | Design user model & schema | Sahaji Chaurasia | Completed | 25-Oct-2025 | 29-Oct-2025
1 | Implement register/login API | Sahaji Chaurasia | Completed | 25-Oct-2025 | 29-Oct-2025
2 | Create artist model | Sahaji Chaurasia | Completed | 25-Oct-2025 | 29-Oct-2025
2 | Develop profile controller | Sahaji Chaurasia | Completed | 25-Oct-2025 | 29-Oct-2025
2 | Test profile creation | Sahaji Chaurasia | Completed | 25-Oct-2025 | 29-Oct-2025
3 | Design artwork schema | Sahaji Chaurasia | Completed | 25-Oct-2025 | 29-Oct-2025
3 | Integrate image upload logic | Sahaji Chaurasia | Completed | 25-Oct-2025 | 29-Oct-2025
3 | Add edit/delete artwork feature | Sahaji Chaurasia | In Progress | 25-Oct-2025 | 29-Oct-2025

## Sprint 2 Backlog
Story ID | Task | Assignee | Status | Start Date | End Date
4 | Implement search filters | Sahaji Chaurasia | Completed | 30-Oct-2025 | 03-Nov-2025
4 | Add artwork suggestions | Sahaji Chaurasia | Completed | 30-Oct-2025 | 03-Nov-2025
5 | Create order model & schema | Sahaji Chaurasia | Completed | 30-Oct-2025 | 03-Nov-2025
5 | Integrate Razorpay/Stripe API | Sahaji Chaurasia | In Progress | 30-Oct-2025 | 03-Nov-2025
6 | Build analytics dashboard UI | Sahaji Chaurasia | Completed | 30-Oct-2025 | 03-Nov-2025
6 | Integrate charts with data | Sahaji Chaurasia | Completed | 30-Oct-2025 | 03-Nov-2025
7 | Design community post schema | Sahaji Chaurasia | In Progress | 30-Oct-2025 | 03-Nov-2025
7 | Implement comment & like features | Sahaji Chaurasia | In Progress | 30-Oct-2025 | 03-Nov-2025

## Stand-up Log
Date | Task Summary | Status | Next Plan | Blockers
25-Oct-2025 | Setup backend structure and repo initialization | Completed | Move to Auth testing | None
26-Oct-2025 | Implement User registration & JWT auth | Completed | Implement validation and error handling | None
27-Oct-2025 | Develop artist profile module | Completed | Integrate profile with auth system | None
28-Oct-2025 | Artwork upload functionality completed | Completed | Finalize artwork CRUD operations | None
29-Oct-2025 | Added artwork search filters and pagination | Completed | Connect search to frontend filters | None
30-Oct-2025 | Integrated purchase flow and Razorpay API | Completed | Complete payment integration tests | None
31-Oct-2025 | Dashboard analytics and charts integrated | Completed | Refine analytics charts | None
01-Nov-2025 | Community post module development | Completed | Debug community post routes | None
02-Nov-2025 | Testing, debugging, and deployment preparation | In Progress | Perform UI testing and prepare for review | None

## Retrospection
What Went Well | What Could Improve | Action Items
Smooth sprint progress and story completion | Better time allocation for frontend tasks | Add Jest unit tests
Effective Git commits and daily pushes | Improve testing documentation | Optimize API response time
Bug fixes handled quickly | Automate deployment for faster iteration | Plan UI review sessions earlier